## Sheet1
Queen Rearing Planner
| Enter Grafting Date |  |  | 2026-09-15
Cell Run Age | Day | Date | Task/Status
(days)
-4 | Monday | 2026-09-07 | Set aside resource (honey and pollen frames) | Preliminary Activities
-3 | Tuesday | 2026-09-08 | Configure Cell Builders (starter and finisher)
-2 | Wednesday | 2026-09-09 | Move dark frame into frame excluder of donating colony
-1 | Thursday | 2026-09-10 | Locate donating queen and move into frame excluder
1 | Friday | 2026-09-11 | Donating queen lays eggs
2 | Saturday | 2026-09-12
3 | Sunday | 2026-09-13 | Eggs hatch/ Pupa stage begins
4 | Monday | 2026-09-14 | Make up cell Starter/Finisher Colony
5 | Tuesday | 2026-09-15 | Graft the day-old larva into cell cups, and insert it into a queenless cell starter colony. | Day 1 (Grafting Day)
6 | Wednesday | 2026-09-16 | Transfer grafting frame to cell finisher | Day 2
7 | Thursday | 2026-09-17
8 | Friday | 2026-09-18 | CHECK GRAFTS: are bees drawing out cells and feeding royal jelly? Yes, Refill feeder and close hive …………………….No, Re-graft | Day 3
9 | Saturday | 2026-09-19
10 | Sunday | 2026-09-20 | Queen cells are capped
11 | Monday | 2026-09-21 | SENSITIVE DEVELOPMENT STAGE
12 | Tuesday | 2026-09-22 | Do not move cells and be very
13 | Wednesday | 2026-09-23 | gentle when in the the hive
14 | Thursday | 2026-09-24 | Make up queenless mating nucs | Day 5
15 | Friday | 2026-09-25 | Transfer queen cells to queenless mating nucs | Day 6
16 | Saturday | 2026-09-26 | Queens emerges
17 | Sunday | 2026-09-27
18 | Monday | 2026-09-28
19 | Tuesday | 2026-09-29 | Discard any unhatched eggs in cells | Day 7
20 | Wednesday | 2026-09-30
21 | Thursday | 2026-10-01 | Mating flights
22 | Friday | 2026-10-02 | Mating flights
23 | Saturday | 2026-10-03
24 | Sunday | 2026-10-04
25 | Monday | 2026-10-05
26 | Tuesday | 2026-10-06
27 | Wednesday | 2026-10-07
28 | Thursday | 2026-10-08
29 | Friday | 2026-10-09
30 | Saturday | 2026-10-10
31 | Sunday | 2026-10-11
32 | Monday | 2026-10-12
33 | Tuesday | 2026-10-13
34 | Wednesday | 2026-10-14
35 | Thursday | 2026-10-15 | Check nucs for eggs | Day 8
36 | Friday | 2026-10-16
37 | Saturday | 2026-10-17
38 | Sunday | 2026-10-18 | Check nucs for larvae | Day 9
39 | Monday | 2026-10-19 | Larvae found? If so, queen has mated
40 | Tuesday | 2026-10-20 | Re-queen if no eggs or larvae found | Day 10
41 | Wednesday | 2026-10-21
42 | Thursday | 2026-10-22
Note: | *Queens mating flights can vary depending on weather conditions. Lower or higher temperatures for example will slow down or speed up process.
*Pay attention to upcoming weather and plan backwards for graft date.
*Queens need between 10-20 drones to mate with her on her flight. (Do you have drones around?)
*Newly mated Queens need about 4 weeks assessment to determine if they have a good brood pattern and have been well mated.